## Phase Overview
Phase | Name | Goal | Backend features | Frontend features | Status
Phase 0 | Foundation | Marketing site + user authentication | 3 | 5 | Done
Phase 1 | MVP — Core Predictions | DB + chart engine + AI agent v1 + first predictions | 8 | 6 | Planned
Phase 2 | Grow | More predictions, matching, reports, payments | 8 | 7 | Planned
Phase 3 | Scale | Specialized agents, live astrologer chat, shop, admin | 8 | 6 | Planned
Phase 4 | Expand | Numerology/KP/Tarot, multi-language, mobile app | 4 | 4 | Planned

## Roadmap
Phase | Phase Name | Side | Feature | Details | Priority | Status
Phase 0 | Foundation | Backend | Auth API (register/login/me) | JWT + bcrypt, validation, duplicate guard | P0 | Done
Phase 0 | Foundation | Backend | CORS + health endpoint | Frontend origin locked, /api/health | P0 | Done
Phase 0 | Foundation | Backend | JSON file user store | Swappable data layer (store.js) | P0 | Done
Phase 0 | Foundation | Frontend | Marketing homepage | Hero, services, zodiac, astrologers, panchang, CTA | P0 | Done
Phase 0 | Foundation | Frontend | Animated cosmic background | Canvas starfield, mobile-optimized | P0 | Done
Phase 0 | Foundation | Frontend | About / Contact / Disclaimer | Tailwind + MUI icons | P1 | Done
Phase 0 | Foundation | Frontend | Login / Register pages | AuthForm + AuthContext, header auth state | P0 | Done
Phase 0 | Foundation | Frontend | Red theme + responsive | Token-based theme, mobile hamburger | P1 | Done
Phase 1 | MVP — Core Predictions | Backend | MongoDB migration | Replace file store with MongoDB (store.js only) | P0 | Planned
Phase 1 | MVP — Core Predictions | Backend | Chart engine integration | Swiss Ephemeris → full kundli + core planets/houses | P0 | Planned
Phase 1 | MVP — Core Predictions | Backend | POST /api/chart | DOB → compute + cache full chart profile | P0 | Planned
Phase 1 | MVP — Core Predictions | Backend | AI Agent v1 (Claude) | Domain prompt + chart grounding + JSON output | P0 | Planned
Phase 1 | MVP — Core Predictions | Backend | Prediction: Kundli summary | POST /api/predict/kundli | P0 | Planned
Phase 1 | MVP — Core Predictions | Backend | Prediction: Love | POST /api/predict/love | P0 | Planned
Phase 1 | MVP — Core Predictions | Backend | Prediction: Marriage | POST /api/predict/marriage (timing, spouse) | P0 | Planned
Phase 1 | MVP — Core Predictions | Backend | Basic paywall check | Free vs paid gating on predictions | P1 | Planned
Phase 1 | MVP — Core Predictions | Frontend | Birth-details form | DOB/time/place + place autocomplete (geocode) | P0 | Planned
Phase 1 | MVP — Core Predictions | Frontend | Kundli display | Chart visual + AI summary cards | P0 | Planned
Phase 1 | MVP — Core Predictions | Frontend | Love prediction page | Form → result cards (score/forecast) | P0 | Planned
Phase 1 | MVP — Core Predictions | Frontend | Marriage prediction page | Timing windows + spouse traits UI | P0 | Planned
Phase 1 | MVP — Core Predictions | Frontend | My Predictions (basic) | List of saved predictions | P1 | Planned
Phase 1 | MVP — Core Predictions | Frontend | Loading / streaming states | Stream AI output to UI | P1 | Planned
Phase 2 | Grow | Backend | RAG knowledge base | Vector DB of classical rules per domain | P0 | Planned
Phase 2 | Grow | Backend | Predictions: Career/Health/Finance | POST /api/predict/:type | P0 | Planned
Phase 2 | Grow | Backend | Predictions: Dasha / Sade Sati | Timing predictions from dasha + transit | P1 | Planned
Phase 2 | Grow | Backend | Kundli Milan (matching) | POST /api/match — Ashtakoot 36 guna | P0 | Planned
Phase 2 | Grow | Backend | Bundled reports | POST /api/report/:kind (PDF gen) | P1 | Planned
Phase 2 | Grow | Backend | Payments + wallet | Razorpay/Stripe, orders, wallet | P0 | Planned
Phase 2 | Grow | Backend | Subscriptions | Daily predictions + chat plan | P1 | Planned
Phase 2 | Grow | Backend | Prediction rating | User feedback loop (for future fine-tune) | P2 | Planned
Phase 2 | Grow | Frontend | Career/Health/Finance pages | Forms + result cards | P0 | Planned
Phase 2 | Grow | Frontend | Kundli Milan (couple form) | Two people → compatibility result | P0 | Planned
Phase 2 | Grow | Frontend | Reports UI + PDF download | Buy → view → download report | P1 | Planned
Phase 2 | Grow | Frontend | Payments / checkout | Wallet + plan checkout flow | P0 | Planned
Phase 2 | Grow | Frontend | User dashboard | Profile, saved charts, reports, wallet | P1 | Planned
Phase 2 | Grow | Frontend | Personalized daily horoscope | Rashifal based on user chart | P1 | Planned
Phase 2 | Grow | Frontend | Rating widget | Thumbs/stars on predictions | P2 | Planned
Phase 3 | Scale | Backend | Specialized sub-agents | Dedicated Love/Marriage/Career agents | P1 | Planned
Phase 3 | Scale | Backend | Talk-to-astrologer chat | Socket.IO real-time chat/call | P0 | Planned
Phase 3 | Scale | Backend | Astrologer management | Onboarding, availability, commission | P0 | Planned
Phase 3 | Scale | Backend | Fine-tune + eval harness | Curated dataset, quality metrics | P1 | Planned
Phase 3 | Scale | Backend | Remedies / shop API | Gemstone/rudraksha/yantra catalog + orders | P1 | Planned
Phase 3 | Scale | Backend | Notifications | Email/push (daily, transit alerts) | P1 | Planned
Phase 3 | Scale | Backend | Security hardening | Rate limiting, refresh tokens | P0 | Planned
Phase 3 | Scale | Backend | Admin API | Manage users, astrologers, content | P1 | Planned
Phase 3 | Scale | Frontend | Real-time chat UI | Chat with astrologer + wallet timer | P0 | Planned
Phase 3 | Scale | Frontend | Astrologer profiles + booking | Browse, filter, book | P0 | Planned
Phase 3 | Scale | Frontend | Shop (gemstones/remedies) | Product listing + cart + checkout | P1 | Planned
Phase 3 | Scale | Frontend | Notifications center | In-app + push opt-in | P1 | Planned
Phase 3 | Scale | Frontend | Admin panel | Dashboard for ops | P1 | Planned
Phase 3 | Scale | Frontend | PWA / installable | Offline shell, add-to-home | P2 | Planned
Phase 4 | Expand | Backend | Numerology / KP / Lal Kitab engines | Additional prediction systems | P1 | Planned
Phase 4 | Expand | Backend | Tarot service | Card-based readings | P2 | Planned
Phase 4 | Expand | Backend | Multi-language content API | Hindi/English + more | P1 | Planned
Phase 4 | Expand | Backend | Recommendation engine | Cross-sell reports/consults | P2 | Planned
Phase 4 | Expand | Frontend | Numerology/KP/Lal Kitab pages | New prediction modules | P1 | Planned
Phase 4 | Expand | Frontend | Tarot + Palmistry | Card UI + hand image upload | P2 | Planned
Phase 4 | Expand | Frontend | Multi-language (i18n) | Language switch | P1 | Planned
Phase 4 | Expand | Frontend | Mobile app | React Native (iOS/Android) | P1 | Planned